## Comment sheet
Comment sheet
Still open points
Commented Document |  | Document Nature | IFR | Title | Kingdom Project
|  | Reception Date |  | Document Number | SHS_KOR-SHR-00019
Last Issue date |  |  |  |  | 09/01/2026 | From | EDFps
Comment Sheet History
Item | Version | Page | Section | From (written by) | Comments | From (responded by) | Responses | Status | Priority (Major,Minor)
1 | 1.0 |  |  |  | Why was the interpretation of H2/T2 done this way in the south east? It seaems the general trend of H2 would have aligned more with the lower set of reflectors (yellow arrow). Same for the erosion T2, it seems it could have been put lower (bue arrow), equivalent to the general trend seen along the line. |  |  | Open
2 | 1.0 |  |  |  | Why isn't the SBP uploaded in the kingdom project? |  |  | Open
3 | 1.0 |  |  |  | Please load the navigation of the lines then import the data insde these geometries. As is the lines geometry is an approximation, constructed typically by a decimation of the shot points |  |  | Open
4 | 1.0 |  |  |  | There are various discrepencies in the horizons interpretations. Granted the stratigraphy is complex and with the sparse line plan it is difficult to keep track for some reflectors, but please adjust for coherency when possible. Exemple below shows discrepencies between displayed line and crosslines (A) and some misinterpreted horizons along given seismic line, cutting though different packages (B).
5 | 1.0 |  |  |  | Please adjust the picking to the 2D Hunt mode when possible. E.g. H1&H2 can be picked by following strong continuous reflectors most the time:
6 | 1.0 |  |  |  | Shallow horizon does not display in base map, is it because the SBP could not be found in the project? The associated grid is available.
7 | 1.0
8 | 1.0
9 | 1.0

## Instructions
Guidance for using the Comments sheet
One comment sheet per document
We keep the same comment sheet for all updates, new revision of the same document
The “Last issue date” and “from” shall be completed by the last issuer.
No modifications are allowed on previous comments.
New version of Contractor’s Documents must be accompanied with its updated Comments Sheet.
Responses shall be indicated in Red beginning with date of response.
Major item (2.0, 3.0,…) = New question/comment
Minor item (1.1, 1.2,…) = question and its responses
Only the Employer can close comments on the Comments Sheet.
Prioriry of comments : Major = major comments ; Minor = Minor comments All Major comments shall be closed before sending a new revision of Deliverable